## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Project Implementation | 95.75 days | June 29, 2018 8:00 AM | November 9, 2018 3:00 PM |  | 0
1 | Yes | Auto Scheduled | Scope | 3.5 days | June 29, 2018 8:00 AM | July 4, 2018 12:00 PM |  | 1
2 | Yes | Auto Scheduled | Determine project scope | 4 hrs | June 29, 2018 8:00 AM | June 29, 2018 12:00 PM |  | 2
3 | Yes | Auto Scheduled | Secure project sponsorship | 1 day | June 29, 2018 1:00 PM | July 2, 2018 12:00 PM | 2 | 2
4 | Yes | Auto Scheduled | Define preliminary resources | 1 day | July 2, 2018 1:00 PM | July 3, 2018 12:00 PM | 3 | 2
5 | Yes | Auto Scheduled | Secure core resources | 1 day | July 3, 2018 1:00 PM | July 4, 2018 12:00 PM | 4 | 2
6 | Yes | Auto Scheduled | Scope complete | 0 days | July 4, 2018 12:00 PM | July 4, 2018 12:00 PM | 5 | 2
7 | Yes | Auto Scheduled | Analysis/Software Requirements | 14 days | July 4, 2018 1:00 PM | July 24, 2018 12:00 PM |  | 1
8 | Yes | Auto Scheduled | Conduct needs analysis | 5 days | July 4, 2018 1:00 PM | July 11, 2018 12:00 PM | 6 | 2
9 | Yes | Auto Scheduled | Draft preliminary software specifications | 3 days | July 11, 2018 1:00 PM | July 16, 2018 12:00 PM | 8 | 2
10 | Yes | Auto Scheduled | Develop preliminary budget | 2 days | July 16, 2018 1:00 PM | July 18, 2018 12:00 PM | 9 | 2
11 | Yes | Auto Scheduled | Review software specifications/budget with team | 4 hrs | July 18, 2018 1:00 PM | July 18, 2018 5:00 PM | 10 | 2
12 | Yes | Auto Scheduled | Incorporate feedback on software specifications | 1 day | July 19, 2018 8:00 AM | July 19, 2018 5:00 PM | 11 | 2
13 | Yes | Auto Scheduled | Develop delivery timeline | 1 day | July 20, 2018 8:00 AM | July 20, 2018 5:00 PM | 12 | 2
14 | Yes | Auto Scheduled | Obtain approvals to proceed (concept, timeline, budget) | 4 hrs | July 23, 2018 8:00 AM | July 23, 2018 12:00 PM | 13 | 2
15 | Yes | Auto Scheduled | Secure required resources | 1 day | July 23, 2018 1:00 PM | July 24, 2018 12:00 PM | 14 | 2
16 | Yes | Auto Scheduled | Analysis complete | 0 days | July 24, 2018 12:00 PM | July 24, 2018 12:00 PM | 15 | 2
17 | Yes | Auto Scheduled | Design | 14.5 days | July 24, 2018 1:00 PM | August 13, 2018 5:00 PM |  | 1
18 | Yes | Auto Scheduled | Review preliminary software specifications | 2 days | July 24, 2018 1:00 PM | July 26, 2018 12:00 PM | 16 | 2
19 | Yes | Auto Scheduled | Develop functional specifications | 5 days | July 26, 2018 1:00 PM | August 2, 2018 12:00 PM | 18 | 2
20 | Yes | Auto Scheduled | Develop prototype based on functional specifications | 4 days | August 2, 2018 1:00 PM | August 8, 2018 12:00 PM | 19 | 2
21 | Yes | Auto Scheduled | Review functional specifications | 2 days | August 8, 2018 1:00 PM | August 10, 2018 12:00 PM | 20 | 2
22 | Yes | Auto Scheduled | Incorporate feedback into functional specifications | 1 day | August 10, 2018 1:00 PM | August 13, 2018 12:00 PM | 21 | 2
23 | Yes | Auto Scheduled | Obtain approval to proceed | 4 hrs | August 13, 2018 1:00 PM | August 13, 2018 5:00 PM | 22 | 2
24 | Yes | Auto Scheduled | Design complete | 0 days | August 13, 2018 5:00 PM | August 13, 2018 5:00 PM | 23 | 2
25 | Yes | Auto Scheduled | Development | 21.75 days | August 14, 2018 8:00 AM | September 12, 2018 3:00 PM |  | 1
26 | Yes | Auto Scheduled | Review functional specifications | 1 day | August 14, 2018 8:00 AM | August 14, 2018 5:00 PM | 24 | 2
27 | Yes | Auto Scheduled | Identify modular/tiered design parameters | 1 day | August 15, 2018 8:00 AM | August 15, 2018 5:00 PM | 26 | 2
28 | Yes | Auto Scheduled | Assign development staff | 1 day | August 16, 2018 8:00 AM | August 16, 2018 5:00 PM | 27 | 2
29 | Yes | Auto Scheduled | Develop code | 15 days | August 17, 2018 8:00 AM | September 6, 2018 5:00 PM | 28 | 2
30 | Yes | Auto Scheduled | Developer testing (primary debugging) | 15 days | August 22, 2018 3:00 PM | September 12, 2018 3:00 PM | 29FS-75% | 2
31 | Yes | Auto Scheduled | Development complete | 0 days | September 12, 2018 3:00 PM | September 12, 2018 3:00 PM | 30 | 2
32 | Yes | Auto Scheduled | Testing | 48.75 days | August 14, 2018 8:00 AM | October 19, 2018 3:00 PM |  | 1
33 | Yes | Auto Scheduled | Develop unit test plans using product specifications | 4 days | August 14, 2018 8:00 AM | August 17, 2018 5:00 PM | 24 | 2
34 | Yes | Auto Scheduled | Develop integration test plans using product specifications | 4 days | August 14, 2018 8:00 AM | August 17, 2018 5:00 PM | 24 | 2
35 | Yes | Auto Scheduled | Unit Testing | 15 days | September 12, 2018 3:00 PM | October 3, 2018 3:00 PM |  | 2
36 | Yes | Auto Scheduled | Review modular code | 5 days | September 12, 2018 3:00 PM | September 19, 2018 3:00 PM | 33,31 | 3
37 | Yes | Auto Scheduled | Test component modules to product specifications | 2 days | September 19, 2018 3:00 PM | September 21, 2018 3:00 PM | 31,36 | 3
38 | Yes | Auto Scheduled | Identify anomalies to product specifications | 3 days | September 21, 2018 3:00 PM | September 26, 2018 3:00 PM | 37 | 3
39 | Yes | Auto Scheduled | Modify code | 3 days | September 26, 2018 3:00 PM | October 1, 2018 3:00 PM | 38 | 3
40 | Yes | Auto Scheduled | Re-test modified code | 2 days | October 1, 2018 3:00 PM | October 3, 2018 3:00 PM | 39 | 3
41 | Yes | Auto Scheduled | Unit testing complete | 0 days | October 3, 2018 3:00 PM | October 3, 2018 3:00 PM | 40 | 3
42 | Yes | Auto Scheduled | Integration Testing | 12 days | October 3, 2018 3:00 PM | October 19, 2018 3:00 PM |  | 2
43 | Yes | Auto Scheduled | Test module integration | 5 days | October 3, 2018 3:00 PM | October 10, 2018 3:00 PM | 41 | 3
44 | Yes | Auto Scheduled | Identify anomalies to specifications | 2 days | October 10, 2018 3:00 PM | October 12, 2018 3:00 PM | 43 | 3
45 | Yes | Auto Scheduled | Modify code | 3 days | October 12, 2018 3:00 PM | October 17, 2018 3:00 PM | 44 | 3
46 | Yes | Auto Scheduled | Re-test modified code | 2 days | October 17, 2018 3:00 PM | October 19, 2018 3:00 PM | 45 | 3
47 | Yes | Auto Scheduled | Integration testing complete | 0 days | October 19, 2018 3:00 PM | October 19, 2018 3:00 PM | 46 | 3
48 | Yes | Auto Scheduled | Training | 45.75 days | August 14, 2018 8:00 AM | October 16, 2018 3:00 PM |  | 1
49 | Yes | Auto Scheduled | Develop training specifications for end users | 3 days | August 14, 2018 8:00 AM | August 16, 2018 5:00 PM | 24 | 2
50 | Yes | Auto Scheduled | Develop training specifications for helpdesk support staff | 3 days | August 14, 2018 8:00 AM | August 16, 2018 5:00 PM | 24 | 2
51 | Yes | Auto Scheduled | Identify training delivery methodology (computer based training, classroom, etc.) | 2 days | August 14, 2018 8:00 AM | August 15, 2018 5:00 PM | 24 | 2
52 | Yes | Auto Scheduled | Develop training materials | 3 wks | September 12, 2018 3:00 PM | October 3, 2018 3:00 PM | 49,31,50,51 | 2
53 | Yes | Auto Scheduled | Conduct training usability study | 4 days | October 3, 2018 3:00 PM | October 9, 2018 3:00 PM | 52 | 2
54 | Yes | Auto Scheduled | Finalize training materials | 3 days | October 9, 2018 3:00 PM | October 12, 2018 3:00 PM | 53 | 2
55 | Yes | Auto Scheduled | Develop training delivery mechanism | 2 days | October 12, 2018 3:00 PM | October 16, 2018 3:00 PM | 54 | 2
56 | Yes | Auto Scheduled | Training materials complete | 0 days | October 16, 2018 3:00 PM | October 16, 2018 3:00 PM | 55 | 2
57 | Yes | Auto Scheduled | Documentation | 30.5 days | August 14, 2018 8:00 AM | September 25, 2018 12:00 PM |  | 1
58 | Yes | Auto Scheduled | Develop Help specification | 1 day | August 14, 2018 8:00 AM | August 14, 2018 5:00 PM | 24 | 2
59 | Yes | Auto Scheduled | Develop Help system | 3 wks | August 28, 2018 1:00 PM | September 18, 2018 12:00 PM | 58,29FS-50% | 2
60 | Yes | Auto Scheduled | Review Help documentation | 3 days | September 18, 2018 1:00 PM | September 21, 2018 12:00 PM | 59 | 2
61 | Yes | Auto Scheduled | Incorporate Help documentation feedback | 2 days | September 21, 2018 1:00 PM | September 25, 2018 12:00 PM | 60 | 2
62 | Yes | Auto Scheduled | Develop user manuals specifications | 2 days | August 14, 2018 8:00 AM | August 15, 2018 5:00 PM | 24 | 2
63 | Yes | Auto Scheduled | Develop user manuals | 3 wks | August 28, 2018 1:00 PM | September 18, 2018 12:00 PM | 62,29FS-50% | 2
64 | Yes | Auto Scheduled | Review all user documentation | 2 days | September 18, 2018 1:00 PM | September 20, 2018 12:00 PM | 63 | 2
65 | Yes | Auto Scheduled | Incorporate user documentation feedback | 2 days | September 20, 2018 1:00 PM | September 24, 2018 12:00 PM | 64 | 2
66 | Yes | Auto Scheduled | Documentation complete | 0 days | September 25, 2018 12:00 PM | September 25, 2018 12:00 PM | 65,61 | 2
67 | Yes | Auto Scheduled | Pilot | 70.25 days | July 24, 2018 1:00 PM | October 30, 2018 3:00 PM |  | 1
68 | Yes | Auto Scheduled | Identify test group | 1 day | July 24, 2018 1:00 PM | July 25, 2018 12:00 PM | 16 | 2
69 | Yes | Auto Scheduled | Develop software delivery mechanism | 1 day | July 25, 2018 1:00 PM | July 26, 2018 12:00 PM | 68 | 2
70 | Yes | Auto Scheduled | Install/deploy software | 1 day | October 19, 2018 3:00 PM | October 22, 2018 3:00 PM | 47,69,66,56 | 2
71 | Yes | Auto Scheduled | Obtain user feedback | 1 wk | October 22, 2018 3:00 PM | October 29, 2018 3:00 PM | 70 | 2
72 | Yes | Auto Scheduled | Evaluate testing information | 1 day | October 29, 2018 3:00 PM | October 30, 2018 3:00 PM | 71 | 2
73 | Yes | Auto Scheduled | Pilot complete | 0 days | October 30, 2018 3:00 PM | October 30, 2018 3:00 PM | 72 | 2
74 | Yes | Auto Scheduled | Deployment | 5 days | October 30, 2018 3:00 PM | November 6, 2018 3:00 PM |  | 1
75 | Yes | Auto Scheduled | Determine final deployment strategy | 1 day | October 30, 2018 3:00 PM | October 31, 2018 3:00 PM | 73 | 2
76 | Yes | Auto Scheduled | Develop deployment methodology | 1 day | October 31, 2018 3:00 PM | November 1, 2018 3:00 PM | 75 | 2
77 | Yes | Auto Scheduled | Secure deployment resources | 1 day | November 1, 2018 3:00 PM | November 2, 2018 3:00 PM | 76 | 2
78 | Yes | Auto Scheduled | Train support staff | 1 day | November 2, 2018 3:00 PM | November 5, 2018 3:00 PM | 77 | 2
79 | Yes | Auto Scheduled | Deploy software | 1 day | November 5, 2018 3:00 PM | November 6, 2018 3:00 PM | 78 | 2
80 | Yes | Auto Scheduled | Deployment complete | 0 days | November 6, 2018 3:00 PM | November 6, 2018 3:00 PM | 79 | 2
81 | Yes | Auto Scheduled | Post Implementation Review | 3 days | November 6, 2018 3:00 PM | November 9, 2018 3:00 PM |  | 1
82 | Yes | Auto Scheduled | Document lessons learned | 1 day | November 6, 2018 3:00 PM | November 7, 2018 3:00 PM | 80 | 2
83 | Yes | Auto Scheduled | Distribute to team members | 1 day | November 7, 2018 3:00 PM | November 8, 2018 3:00 PM | 82 | 2
84 | Yes | Auto Scheduled | Create software maintenance team | 1 day | November 8, 2018 3:00 PM | November 9, 2018 3:00 PM | 83 | 2
85 | Yes | Auto Scheduled | Post implementation review complete | 0 days | November 9, 2018 3:00 PM | November 9, 2018 3:00 PM | 84 | 2
86 | Yes | Auto Scheduled | Software development template complete | 0 days | November 9, 2018 3:00 PM | November 9, 2018 3:00 PM | 85 | 1

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Management | M | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Project Manager | P | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Analyst | A | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Developer | D | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Testers | T | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Trainers | T | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Technical Communicators | T | Work |  |  |  |  | 100% | $0.00/h | 0
8 | Deployment Team | D | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Determine project scope | Management | 0 | 4h | 100%
Secure project sponsorship | Management | 0 | 8h | 100%
Define preliminary resources | Project Manager | 0 | 8h | 100%
Secure core resources | Project Manager | 0 | 8h | 100%
Conduct needs analysis | Analyst | 0 | 40h | 100%
Draft preliminary software specifications | Analyst | 0 | 24h | 100%
Develop preliminary budget | Project Manager | 0 | 16h | 100%
Review software specifications/budget with team | Project Manager | 0 | 4h | 100%
Review software specifications/budget with team | Analyst | 0 | 4h | 100%
Incorporate feedback on software specifications | Analyst | 0 | 8h | 100%
Develop delivery timeline | Project Manager | 0 | 8h | 100%
Obtain approvals to proceed (concept, timeline, budget) | Management | 0 | 4h | 100%
Obtain approvals to proceed (concept, timeline, budget) | Project Manager | 0 | 4h | 100%
Secure required resources | Project Manager | 0 | 8h | 100%
Review preliminary software specifications | Analyst | 0 | 16h | 100%
Develop functional specifications | Analyst | 0 | 40h | 100%
Develop prototype based on functional specifications | Analyst | 0 | 32h | 100%
Review functional specifications | Management | 0 | 16h | 100%
Incorporate feedback into functional specifications | Management | 0 | 8h | 100%
Obtain approval to proceed | Management | 0 | 4h | 100%
Obtain approval to proceed | Project Manager | 0 | 4h | 100%
Review functional specifications | Developer | 0 | 8h | 100%
Identify modular/tiered design parameters | Developer | 0 | 8h | 100%
Assign development staff | Developer | 0 | 8h | 100%
Develop code | Developer | 0 | 120h | 100%
Developer testing (primary debugging) | Developer | 0 | 120h | 100%
Develop unit test plans using product specifications | Testers | 0 | 32h | 100%
Develop integration test plans using product specifications | Testers | 0 | 32h | 100%
Review modular code | Testers | 0 | 40h | 100%
Test component modules to product specifications | Testers | 0 | 16h | 100%
Identify anomalies to product specifications | Testers | 0 | 24h | 100%
Modify code | Testers | 0 | 24h | 100%
Re-test modified code | Testers | 0 | 16h | 100%
Test module integration | Testers | 0 | 40h | 100%
Identify anomalies to specifications | Testers | 0 | 16h | 100%
Modify code | Testers | 0 | 24h | 100%
Re-test modified code | Testers | 0 | 16h | 100%
Develop training specifications for end users | Trainers | 0 | 24h | 100%
Develop training specifications for helpdesk support staff | Trainers | 0 | 24h | 100%
Identify training delivery methodology (computer based training, classroom, etc.) | Trainers | 0 | 16h | 100%
Develop training materials | Trainers | 0 | 120h | 100%
Conduct training usability study | Trainers | 0 | 32h | 100%
Finalize training materials | Trainers | 0 | 24h | 100%
Develop training delivery mechanism | Trainers | 0 | 16h | 100%
Develop Help specification | Technical Communicators | 0 | 8h | 100%
Develop Help system | Technical Communicators | 0 | 120h | 100%
Review Help documentation | Technical Communicators | 0 | 24h | 100%
Incorporate Help documentation feedback | Technical Communicators | 0 | 16h | 100%
Develop user manuals specifications | Technical Communicators | 0 | 16h | 100%
Develop user manuals | Technical Communicators | 0 | 120h | 100%
Review all user documentation | Technical Communicators | 0 | 16h | 100%
Incorporate user documentation feedback | Technical Communicators | 0 | 16h | 100%
Identify test group | Project Manager | 0 | 8h | 100%
Install/deploy software | Deployment Team | 0 | 8h | 100%
Obtain user feedback | Deployment Team | 0 | 40h | 100%
Evaluate testing information | Deployment Team | 0 | 8h | 100%
Determine final deployment strategy | Deployment Team | 0 | 8h | 100%
Develop deployment methodology | Deployment Team | 0 | 8h | 100%
Secure deployment resources | Deployment Team | 0 | 8h | 100%
Train support staff | Deployment Team | 0 | 8h | 100%
Deploy software | Deployment Team | 0 | 8h | 100%
Document lessons learned | Project Manager | 0 | 8h | 100%
Distribute to team members | Project Manager | 0 | 8h | 100%
Create software maintenance team | Project Manager | 0 | 8h | 100%